## Project Overview
IIS Centralized Certificate Implementation Plan
Project Information
Project Name: | IIS Centralized Certificate Store Implementation
Objective: | Implement centralized certificate management across Node 1 and Node 2
Environment: | Production IIS Web Farm with F5 Load Balancer
Impact: | High - Affects certificate management and load balancing
Estimated Duration: | 4-6 hours
Maintenance Window: | Required - Service interruption expected
Architecture Overview
Component | Current State | Target State | Change Required | Impact Level | Notes
F5 Load Balancer | Load Balancing Mode | Active/Passive Mode | Configuration Change | High | Service interruption during switch
Node 1 (Primary) | Local Certificates | Centralized Cert Store | IIS Configuration | Medium | Primary certificate host
Node 2 (Secondary) | Local Certificates | Centralized Cert Store | IIS Configuration | Medium | Secondary certificate host
SMB Share | Not Configured | Configured & Accessible | Infrastructure Setup | Low | For certificate sharing
Scheduled Tasks | Not Configured | Active Monitoring | Task Scheduler Setup | Low | UNC path monitoring
Project Summary
Total Prerequisites: | 10
Total Implementation Tasks: | 12
Total Validation Steps: | 10
Estimated Total Duration: | 225 minutes

## Prerequisites
Prerequisites Checklist
ID | Prerequisite Item | Description | Owner | Status | Completion Date | Notes
PRE-01 | Request SMB Share | Request and configure SMB share for certificate storage and synchronization between nodes | Infrastructure Team | Pending |  | Must be accessible from both nodes
PRE-02 | SMB Share Permissions | Configure appropriate read/write permissions for IIS service accounts on both nodes | Infrastructure Team | Pending |  | Service accounts need full access
PRE-03 | Network Connectivity Test | Verify network connectivity between nodes and SMB share | Network Team | Pending |  | Test UNC path accessibility
PRE-04 | Schedule Task Setup - Node 1 | Setup scheduled task to check and remap UNC path on Node 1 | System Admin | Pending |  | Monitor every 15 minutes
PRE-05 | Schedule Task Setup - Node 2 | Setup scheduled task to check and remap UNC path on Node 2 | System Admin | Pending |  | Monitor every 15 minutes
PRE-06 | F5 Configuration Backup | Create backup of current F5 load balancer configuration | Network Team | Pending |  | Required before mode change
PRE-07 | F5 Virtual Server Mode Change | Change F5 virtual server from load balancing to active/passive mode | Network Team | Pending |  | Critical - affects traffic routing
PRE-08 | Service Account Verification | Verify IIS service accounts have necessary permissions | Security Team | Pending |  | Required for certificate access
PRE-09 | Maintenance Window Approval | Obtain approval for maintenance window | Change Management | Pending |  | Business approval required
PRE-10 | Rollback Plan Review | Review and approve rollback procedures | Technical Lead | Pending |  | Must be tested and documented

## Implementation Tasks
Implementation Tasks
Task ID | Task Description | Node/Component | Commands/Scripts | Duration (min) | Dependencies | Success Criteria | Notes
IMPL-01 | Copy Required Packages and Scripts to Node 1 Setup_CCS_and_Task.ps1 credentialmanager.2.0.0.nupkg Export_Cert_CCS_Secure.ps1 UNC-Connectivity-Checker.ps1 | Node 1 | Copy-Item -Path "\\source\packages\*" -Destination "C:\IISCerts\" -Recurse | 15 | PRE-01, PRE-02 | All files copied successfully | Includes PowerShell scripts and certificates
IMPL-02 | Run PowerShell Setup Script on Node 1 | Node 1 | PowerShell.exe -ExecutionPolicy Bypass -File "C:\IISCerts\Setup-CentralizedCerts.ps1" | 20 | IMPL-01 | Task scheduler entry created, IIS centralized certificate enabled | Script configures certificate export task
IMPL-03 | Configure IIS Centralized Certificate Store - Node 1 | Node 1 | Enable-IISCentralCertProvider -CertStoreLocation "\\share\certs" -UserName "domain\svc_iis" -Password $securePassword | 10 | IMPL-02 | Centralized certificate store enabled | Requires service account credentials
IMPL-04 | Update IIS Bindings to Use Centralized Store - Node 1 | Node 1 | Set-WebBinding -Name "Default Web Site" -BindingInformation "*:443:" -Protocol https -CertificateStoreName "CentralCertStore" | 15 | IMPL-03 | All HTTPS bindings updated | Update all sites with SSL bindings
IMPL-05 | Copy Required Packages and Scripts to Node 2 | Node 2 | Copy-Item -Path "\\source\packages\*" -Destination "C:\IISCerts\" -Recurse | 15 | IMPL-01 | All files copied successfully | Same packages as Node 1
IMPL-06 | Run Node Setup Script on Node 2 | Node 2 | PowerShell.exe -ExecutionPolicy Bypass -File "C:\IISCerts\Setup-Node2-CentralizedCerts.ps1" | 20 | IMPL-05 | IIS centralized certificate store configured | Node 2 specific configuration
IMPL-07 | Configure IIS Centralized Certificate Store - Node 2 | Node 2 | Enable-IISCentralCertProvider -CertStoreLocation "\\share\certs" -UserName "domain\svc_iis" -Password $securePassword | 10 | IMPL-06 | Centralized certificate store enabled | Same configuration as Node 1
IMPL-08 | Update IIS Bindings to Use Centralized Store - Node 2 | Node 2 | Set-WebBinding -Name "Default Web Site" -BindingInformation "*:443:" -Protocol https -CertificateStoreName "CentralCertStore" | 15 | IMPL-07 | All HTTPS bindings updated | Mirror Node 1 configuration
IMPL-09 | Test Certificate Access from Both Nodes | Both Nodes | Test-Path "\\share\certs\*.pfx" ; Get-IISCentralCertProvider | 10 | IMPL-04, IMPL-08 | Certificates accessible from both nodes | Verify UNC path and certificate loading
IMPL-10 | Validate HTTPS Functionality | Both Nodes | Invoke-WebRequest -Uri "https://localhost" -UseBasicParsing | 10 | IMPL-09 | HTTPS sites respond correctly | Test all SSL-enabled sites
IMPL-11 | Switch F5 to Active/Passive Mode | F5 Load Balancer | Configure virtual server pool members with priority settings | 15 | IMPL-10 | Traffic routing to active node only | Node 1 as active, Node 2 as passive
IMPL-12 | Final End-to-End Testing | All Components | Test complete traffic flow and certificate functionality | 20 | IMPL-11 | All services operational in new configuration | Comprehensive functionality test

## Timeline & Dependencies
Project Timeline & Dependencies
Phase 1: Prerequisites (Day 1-3)
Task | Duration | Start Day | Dependencies | Critical Path | Owner
SMB Share Setup | 4 hours | Day 1 | None | Yes | Infrastructure Team
Network Connectivity | 2 hours | Day 1 | SMB Share Setup | Yes | Network Team
Scheduled Tasks Setup | 3 hours | Day 2 | SMB Share Setup | No | System Admin
F5 Configuration Backup | 1 hour | Day 2 | None | Yes | Network Team
Service Account Setup | 2 hours | Day 2 | SMB Share Setup | No | Security Team
Phase 2: Implementation (Day 4)
Task | Duration | Start Time | Dependencies | Critical Path | Owner
Node 1 Setup | 60 min | 09:00 | All Prerequisites | Yes | System Admin
Node 1 Testing | 20 min | 10:00 | Node 1 Setup | Yes | System Admin
Node 2 Setup | 60 min | 10:30 | Node 1 Testing | Yes | System Admin
Node 2 Testing | 20 min | 11:30 | Node 2 Setup | Yes | System Admin
F5 Mode Switch | 15 min | 12:00 | Both Nodes Ready | Yes | Network Team
Final Testing | 30 min | 12:15 | F5 Mode Switch | Yes | Technical Lead

## Validation & Rollback
Validation Steps & Rollback Procedures
Validation Checklist
Check ID | Validation Step | Expected Result | Command/Method | Status
VAL-01 | SMB Share Accessibility | UNC path accessible from both nodes | Test-Path "\\share\certs" | Pending
VAL-02 | Centralized Certificate Store Status | IIS Central Cert Provider enabled | Get-IISCentralCertProvider | Pending
VAL-03 | Certificate Loading | Certificates load from central store | Get-ChildItem "\\share\certs\*.pfx" | Pending
VAL-04 | HTTPS Binding Configuration | All sites use centralized certificates | Get-WebBinding ¦ Where Protocol -eq "https" | Pending
VAL-05 | Website Functionality | All HTTPS sites respond correctly | Invoke-WebRequest -Uri "https://sitename" | Pending
VAL-06 | F5 Load Balancer Mode | Active/Passive mode operational | Check F5 virtual server configuration | Pending
VAL-07 | Scheduled Task Operation | UNC path monitoring tasks running | Get-ScheduledTask -TaskName "*UNCPath*" | Pending
VAL-08 | Certificate Synchronization | Certificates sync between nodes | Compare certificate stores | Pending
VAL-09 | Failover Testing | Passive node can become active | Simulate Node 1 failure | Pending
VAL-10 | Performance Validation | No performance degradation | Monitor response times | Pending
Rollback Procedures
Step | Rollback Action | Component | Command/Procedure | Verification
RB-01 | Restore F5 Load Balancing Mode | F5 Load Balancer | Restore from configuration backup | Traffic distributes to both nodes
RB-02 | Disable Centralized Certificates - Node 1 | Node 1 | Disable-IISCentralCertProvider | Local certificates used
RB-03 | Restore Original IIS Bindings - Node 1 | Node 1 | Restore from IIS configuration backup | Original SSL bindings active
RB-04 | Disable Centralized Certificates - Node 2 | Node 2 | Disable-IISCentralCertProvider | Local certificates used
RB-05 | Restore Original IIS Bindings - Node 2 | Node 2 | Restore from IIS configuration backup | Original SSL bindings active
RB-06 | Remove Scheduled Tasks | Both Nodes | Unregister-ScheduledTask | UNC monitoring tasks removed
RB-07 | Validate Original Functionality | All Components | Test all websites and services | All services operational
RB-08 | Clean Up Installation Files | Both Nodes | Remove-Item "C:\IISCerts\" -Recurse | Installation files removed

## Sheet1
$action = New-ScheduledTaskAction -Execute 'powershell.exe' -Argument '-WindowStyle Hidden -ExecutionPolicy Bypass -File "C:\Scripts\UNC-Connectivity-Checker.ps1"'
$trigger = New-ScheduledTaskTrigger -AtStartup
$tempTrigger = New-ScheduledTaskTrigger -Once -At (Get-Date) -RepetitionInterval (New-TimeSpan -Hours 1)
$trigger.Repetition = $tempTrigger.Repetition
$principal = New-ScheduledTaskPrincipal -GroupId "NT AUTHORITY\SYSTEM" -RunLevel Highest
$settings = New-ScheduledTaskSettingsSet
Register-ScheduledTask -TaskName "UNC Connectivity Checker 2" -Action $action -Trigger $trigger -Principal $principal -Settings $settings -Description "Runs a PowerShell script hourly after system startup."